| School: | Bunn Elementary School |  |  |
| --- | --- | --- | --- |
| School Specific Goal (must be measurable) **One goal must address the TSI-identified subgroup. | Strategies/Action Steps | Timeline for Monitoring | Evidence of Progress/Goal Mastery |
| By June of 2023, as measured by our proficiency goal, Bunn Elementary School will meet the following proficiency goals: 3rd Math: 60%; 4th Math: 60%; 5th Math: 60%. 3rd Reading: 40%; 4th Reading: 40%; 5th Reading: 50%. 5th Science: 65%. | - Professional Learning Communities (discussion of student behaviors, MTSS, Common planning) | Weekly-present-June 2023 3-4 Times Per Week | PLC minutes |
|  | - Common Formative Assessments | Quarterly | Check Ins, i-Ready, mCLASS |
|  | - Data Talks (Data Talk discussions centered around short cycle assessment results and how instructions will be adjusted to student needs) | Weekly-present-June 2023 | Data Talks minutes |
| By June of 2023, Bunn Elementary will decrease discipline referrals by at least 10% from the 2018-2019 referral numbers. | - Administration team will share behavior and referral data quarterly with the entire staff. | Quarterly | Referral data from Educator Handbook |
|  | - Implementation of MTSS behavior plans | Monthly | MTSS Behavior plans |
|  | - Simplify Flowchart for “When to Call an Administrator (Differences in minors and majors) | December 2022 | New flowchart for BES |
|  | - Monitor exclusionary discipline by subgroup- provide feedback to staff where needed | December 22 and May 23 | DATA - Ed Handbook |
| By June 2023, Bunn Elementary School students, staff and community will communicate openly, participate in community events created by BES committees and consistently celebrate successes throughout the school. | - Create committees that provide and organize events and activities that increase parent/community involvement | Nov 2022 | BES Committees |
|  | - Celebrate successes of students, staff and community as publicly. (Principal's weekly newsletter, email/text message blasts and our school sign) | June 2023 | Newsletters, emails, and other messages |
|  | - Promote whole staff community engagement through celebrations and “family” meals - BESt Committee | June 2023 | Family Meal Calendar Creation |
|  | - Open communication to prompt unity with the school community. (Principal weekly newsletters, grade level meetings)- Increase PTA Involvement | June 2023 | PLC minutes and newsletters- PTA Partnerships\ |

| By June 2023, Bunn Elementary will offer multiple opportunities for parents and families to engage in curriculum nights to increase their ability to support student learning and success. | - Plan and implement a school wide curriculum night providing parents and families with take home activities to support their students. Each grade level will look different based on need. | Nov 2022 | Attendance for curriculum night, photos of parents using activities at home. |
| --- | --- | --- | --- |
|  | - Plan and implement Perusing in Pajamas family event providing parents with additional activities for further support. | March 2023 | Attendance for Perusing in Pajamas |
|  | - Provide families with materials to assist them with supporting their students to improve overall achievement in school. | June 2022 | Materials distributed to families, |
|  | - Provide families with detailed information about Reading Plans to be implemented in the 2nd quarter and what that means for their students. | June 2022 | Slides presented to parents, Reading Plans created in 2nd Quarter |

| By June 2023, BES will increase staff participation in school wide staff events by 12%. This will be a 35% staff participation for a staff school wide event. | - Plan and offer staff wide “social” activities to promote positive relationships throughout the building. | June 2023 | Participation in activities |
| --- | --- | --- | --- |
|  | - Promote whole staff community engagement through celebrations and “family” meals | June 2023 | Family Meal Calendar Creation |